## 16-Jan-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP16012025
| Deployment Date | 16-01-2025
| Bug Sheet Attachment | YES
| Maintained By | DurgaDas
S.No. | Release | Modified By | Bug No. | Changes in Module/Submodule | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Attendance Module-Geo Fencing |  | New Request | Mobile | 16-01-25
2 |  | Mitesh |  | Attendance Module-Single punch in & punch out button |  | Modifications | Mobile | 16-01-25
3 |  | Manish |  | Attendance Calendar-User Interface UI changes |  | Modifications | Mobile | 16-01-25
4 | Version 1.0.0+6 | Manish |  | Holiday List-Counting the holiday day |  | Modifications | Mobile | 16-01-25
5 | (Android) | Mitesh |  | Employee Profile-Dynamic Side Bar |  | Modifications | Mobile | 16-01-25
6 |  | Mitesh |  | Leave Management-apply the leave |  | Modifications | Mobile | 16-01-25
| Project Manager |  |  |  |  | MD Signature
|  |  | Bug Sheet Link | Bug Sheet Link

## 20-Jan-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BFDP_20012025
| Deployment Date | 2025-01-20
| Bug Sheet Attachment | YES
| Maintained By | DurgaDas
S.No. | Release | Modified By | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish | Geo-Fencing-Google matrix API Remove use the Geo-Locator & Geo-Coder |  | Modification | Mobile | 20-01-25
2 |  | Mitesh | Attendance-Single check in & check out button |  | Modification | Mobile | 20-01-25
3 |  | Manish | User Interface (UI) changes in Attendance calendar & Logs |  | Modification | Mobile | 20-01-25
4 | Version 1.0.1+7 | Manish | Attendance-check the camera angle |  | Modification | Mobile | 20-01-25
5 | (Android) | Chaitanya | Playstore-Auto update code |  | Modification | Mobile | 20-01-25
6 |  | Manish | TA/DA-Expense code |  | New Request | Mobile | 20-01-25
| Project Manager |  |  |  | MD Signature
| Bug Sheet Link | Bug Sheet Link

## 4-Feb-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP04022025
| Deployment Date | 2025-02-04
| Bug Sheet Attachment | Yes
| Maintained By | DurgaDas
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Major bug fixes and improvements |  | Modifications | Mobile | 2025-02-04
2 |  | Mitesh | 215 | Changes in dashboard UI |  | New Request | Mobile | 2025-02-04
3 |  | Manish | 213 | Added codes in Sub expenses |  | New Request | Mobile | 2025-02-04
4 | Version 1.0.2+8 | Manish | 202 | Changes in adding location in local travel |  | New Request | Mobile | 2025-02-04
5 | (IOS & Android) | Manish |  | New changes in approval module |  | Modifications | Mobile | 2025-02-04
6
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 13-Feb-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP13022025
| Deployment Date | 2025-02-13
| Bug Sheet Attachment | YES
| Maintained By | DurgaDas
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Major bug fixes and improvements |  | Modifications | Mobile | 2025-02-13
2 | Version 1.0.3+9 | Manish |  | Added localization support for multiple languages to enhance user experience. |  | New Request | Mobile | 2025-02-13
3 | (IOS & Android) | Manish |  | Made improvements to the Leave section for better usability. |  | Modifications | Mobile | 2025-02-13
4 |  | Manish |  | Added tutorial for new users |  | New Request | Mobile | 2025-02-13
5
6
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 27-Feb-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP27022025
| Deployment Date | 2025-02-27
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Major bug fixes and improvements |  | Modifications | Mobile | 2025-02-27
2 | Version 1.0.4+11 | Manish |  | Added Wifi punch |  | New Request | Mobile | 2025-02-27
3 | (IOS & Android) | Manish |  | Made the camera smooth |  | Modifications | Mobile | 2025-02-27
4 |  | Manish |  | Added employee summary for superadmins |  | New Request | Mobile | 2025-02-27
5
6
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 01-Mar-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP01032025
| Deployment Date | 2025-03-01
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Major bug fixes and improvements |  | Modifications | Mobile | 2025-03-01
2 | Version 1.0.5+12 | Manish |  | UI changes in attendance punch screen |  | New Request | Mobile | 2025-03-01
3 | (IOS & Android) | Manish |  | Single Login Fix |  | Modifications | Mobile | 2025-03-01
4
5
6
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 23-April-25 App
Version Control- FixHR (Production Release)
| Company | FixingDots |  |  |  |  | JKS file link For App Updates - Prod | https://drive.google.com/drive/folders/1fZMrSaKg5TOntJafozmygW6bUzWIX_ou?usp=drive_link
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP23042025
| Deployment Date | 2025-04-23
| Bug Sheet Attachment | YES
| Maintained By | Hemant
| Server | AWS
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Requests>>Mispunch validation Remove | Functionality | Modifications | Mobile | 23-04-2025
2 | Version 1.0.0 + 1 | Manish |  | Home page loading time. | ( API optimization ) | Modifications | Mobile | 23-04-2025
3 | (IOS & Android) | Manish |  | Location on/off for fixhr | not required now in every condition | Modifications | Mobile | 23-04-2025
4 | (IOS 1.0.3 +4) | Manish |  | TA/DA Eligibility decimal numbers Bug Resolved |  | Error | Mobile | 23-04-2025
5 |  | Manish |  | Approval Search Bar all fields | Functionality | Modifications | Mobile | 23-04-2025
6 |  | Manish |  | TADA Claim report | Functionality | New Request | Mobile | 23-04-2025
Manish
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 17-Mar-2025 App
Version Control- FixHR
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP17032025
| Deployment Date | 2025-03-17
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Chaitanya |  | Major bug fixes and improvements |  | Modifications | Mobile | 2025-03-17
2 | Version 1.0.6+13 | Chaitanya |  | Changes for new image url |  | Modifications | Mobile | 2025-03-17
3 | (IOS & Android) | Chaitanya |  | Employee summary changes |  | Modifications | Mobile | 2025-03-17
4
5
6
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 04-April-2025 App
Version Control- FixHR (Production Release Application)
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP05052025
| Deployment Date | 2025-04-05
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Showing the Shift type in Work Detail ( Employee Profile) |  | New Request | Mobile | 2025-05-05
2 | Version 1.0.1 | Manish |  | Automation Rules in Employee profile Page |  | New Request | Mobile | 2025-05-05
3 | (Android 1.0.1) | Manish |  | Phone call features |  | New Request | Mobile | 2025-05-05
4 | (IOS 1.0.1) | Manish |  | User interface (UI) change |  | New Request | Mobile | 2025-05-05
5 |  | Manish |  | Major bug fixes and improvements |  | New Request | Mobile | 2025-05-05
6 |  | Manish |  | UI Related bugs fixes and improvements |  | New Request | Mobile | 2025-05-05
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 08-April-2025 App
Version Control- FixHR (UAT-Application)
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP08082025
| Deployment Date | 2025-04-08
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Showing the Shift type in Work Detail ( Employee Profile) |  | New Request | Mobile | 2025-05-05
2 | Version 1.0.1 | Manish |  | Automation Rules in Employee profile Page |  | New Request | Mobile | 2025-05-05
3 |  | Manish |  | Phone call features |  | New Request | Mobile | 2025-05-05
4 | (IOS 1.0.7+14) | Manish |  | User interface (UI) change |  | New Request | Mobile | 2025-05-05
5 |  | Manish |  | Major bug fixes and improvements |  | New Request | Mobile | 2025-05-05
6 |  | Manish |  | FIXHR LOGO CHANGE (Colour) |  | New Request | Mobile | 2025-05-05
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 14-April-25 App
Version Control- FixHR (Production Release)
| Company | FixingDots
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP14042025
| Deployment Date | 2025-04-14
| Bug Sheet Attachment | YES
| Maintained By | Chaitanya
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Showing the Shift type in Work Detail ( Employee Profile) |  | New Request | Mobile | 14-04-2025
2 |  | Manish |  | Automation Rules in Employee profile Page |  | New Request | Mobile | 14-04-2025
3 |  | Manish |  | Phone call features |  | New Request | Mobile | 14-04-2025
4 | (IOS 1.0.3 +4) | Manish |  | User interface (UI) change |  | New Request | Mobile | 14-04-2025
5 |  | Manish |  | Major bug fixes and improvements |  | New Request | Mobile | 14-04-2025
6 |  | Manish |  | FIXHR LOGO CHANGE (Colour) |  | New Request | Mobile | 14-04-2025
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## Beta 23-April-25 App
Version Control- FixHR (Beta Release)
| Company | FixingDots |  |  |  |  | JKS file link For App Updates - Beta | https://drive.google.com/drive/folders/1DBq3qP-DnCk-zbntoaTrGV8qDx0cXeQt?usp=drive_link
| Project Name | FIXHR
| Description | HR
| Created By | Kunal
| Document Date | BF_DP23042025
| Deployment Date | 2025-04-23
| Bug Sheet Attachment | YES
| Maintained By | Hemant
| Server | LIPL
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 |  | Manish |  | Requests>>Mispunch validation Remove | Functionality | Functionality Change | Mobile | 23-04-2025
2 | Version 1.0.2 + 3 | Manish |  | Home page loading time. | ( API optimization ) | Modifications | Mobile | 23-04-2025
3 | (IOS & Android) | Manish |  | Location on/off for fixhr | not required now in every condition | Modifications | Mobile | 23-04-2025
4 | (IOS 1.0.9 + 17) | Manish |  | TA/DA Eligibility decimal numbers Bug Resolved |  | Error | Mobile | 23-04-2025
5 |  | Manish |  | Approval Search Bar all fields | Functionality | Modifications | Mobile | 23-04-2025
6 |  | Manish |  | TADA Claim report | Functionality | New Request | Mobile | 23-04-2025
7 |  | Manish |  | Auto Update |  | New Request | Mobile | 23-04-2025
8 |  | Manish |  | Icon Change |  | New Request | Mobile | 23-04-2025
9 |  | Manish |  | Firebase Crash latiy |  | New Request | Mobile | 23-04-2025
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | Bug Sheet Link

## 31-May-25 (Web)
| Company | FixingDots |  | SERVER:-FIXHR (AWS)
| Project Name | FIXHR
| Description | HR
| Created By | Kunal Sir
| Document Date | BF_DP31052025
| Deployment Date | 2025-05-31
| Bug Sheet Attachment | YES
| Maintained By | Dugradas
| Server | AWS
S.No. | Release | Modified By | Bug Number | Changes in Module | Describe Previous & New Change (in case of change) | Reason of Modification | Deployment of | Push Date (changes) | Tester Signature
1 | Version 1.0 | Khilesh |  | Payroll Module:- 1.Component should not be deletable if it is already used in the Salary Master. 2.Change "Button" label to Add. 3.Change "Name" label to Component. 4.In Deduction, remove the ""Enable/Disable PF"" toggle. 5.Add Search functionality in the Payroll module. 6.Salary Master UI updates needed. 7.Status Filter is not working in Salary Master – fix required. 8.Update UI of Salary Master for better usability. 9.In Employee Payroll, update Import/Export buttons. 10.In Employee Payroll index, update Action and Import/Export button layout. 11.In Employee Payroll, update Date of Salary to be shown as With Effective From(WEF). 12.In Add Payroll, remove the Financial Year field. 13.Add a Search option in Add Payroll. 14.Enable Send Mail functionality with filter support. 15.Date field is not updating – fix required. 16.Role permission issues – review and correct. 17.Filter issues on mobile devices in Mis-punch section – prevent auto-refresh by default. 18.UI of Button on hover changes on each page. Employee Page:- 1.Change the Filter layout for better user experience. 2.Add a filter for Status (Active/Inactive). 3.Date Filter is not working or has a format issue – fix required. |  | Modifications | Web | 31-05-25
2 | Version 1.0 | Amarnath |  | Payroll Module (Additional Updates):- 1.Enable Filter, View, and Download options for Payroll data. 2.Fields such as Basic, DA, HRA, CA, Gross Pay, and Net Pay should be non-editable. 3.Add Revision Message column in the Payroll index. Update Buttons:- 1.The Add button should blink when moused over. 2.On selection, show the button as fully filled. 3.Update the Summary section on the Payroll index page. 4.In Add Payroll, change the Clear button to Recalculate. |  | New Request | Web | 31-05-25
3 | Version 1.0 | Pushpalata/Shubhangi |  | Salary Process Page:- 1.Fix input field alignment and formatting issues. 2.When Financial Year is selected as 2024–2025 Display months from April 2024 to December 2024, and January to March 2025. 3.Add dependency between Financial Year and Month selection. 4.Add Payroll Period From, and rename Name field to Payroll Period Name. 5.Change the date format as per standard (e.g., DD-MM-YYYY or as required). In Add Payroll Period:- 1.Allow selecting Month Start or End Date, with one of them selected by default. 2.For Payroll Type - Monthly, enforce a minimum 30-day gap. 3.For Payroll Type - Weekly, enforce a minimum 6-day gap. 4.For Payroll Type - Daily, enforce a minimum 1-day gap. On the Payroll Card:- 1.Show status as Active if payroll is processed. 2.Show card in grey color if not processed. 3.If any month’s data is missing,disable the Freeze button. 3.Show a popup message indicating missing data. 4.When fetching data, show the selected Month and a popup message indicating data is being fetched. 5.On Save or Update, redirect the user back to the Payroll Index page. |  | Modifications | Web | 31-05-25
4 | Version 1.0 | Shubhangi |  | 1.Create a Master Component (MC) Template Sheet for standardized payroll components. 2.Add support for Adhoc Payments and Deductions entry and processing. 3.Define a basic format for Loan/Advance Deductions, including necessary fields like amount, EMI, start and end date, and deduction status. 4.Implement logic for Late Coming Deductions, based on attendance or punch data. 5.Enable Addition of Deductions on Payslip, ensuring all deductions (including adhoc, loan, and late coming) are reflected clearly. |  | New Request | Web | 31-05-25
| Project Manager |  |  |  |  | MD Signature
|  | Bug Sheet Link |  | https://docs.google.com/spreadsheets/d/1w9sSyvBFNgWD4Rrzg4sY7i1T5dewusuuV-nVjzv5M5c/edit?gid=1306210792#gid=1306210792